## Sheet1
Implementation of different features | Priority | Duration | Deadline | Comments
A start game prompt | Medium | 3 hours | 2021-07-15 | This can be completed after the Add New User function and the Main Game Function
- Create a feature to ask the player if they want play
- Asks if they're a new player
- Opens either "add a new play function" or "start playing function"
An "Add new player" feature | Medium | 5 hours | 2021-07-15 | To be done after main game and list feature. If unable to get this completed due to deadline app can still partially work.
-Ask for users full names and store is a list titled "Names"
-Ask for users questions about facial features and save in appropriate dictionaries
-needs to make sure numbers aren’t entered
- A default list of 20 names and facial features need to generated needed
List feature | High | 6 hours | 2021-07-12 | This will be needed to be completed prior to starting the the main game feature.
-Create a list for names of all the player and fictional character.
- Create a temporary list of all previous and new the player names.
- Creates a list of descritive words used within each facial features dictionay
- Need to ensure that the descritive words aren't repeated within their lists
- A default list of 20 names and facial features need to generated needed
Main game feature | High | 10 hours | 2021-07-14 | Plenty of time needs to be allocated for this.
-Communicate to the user the rules of the game
- It will need to be able to generate questions with a randon feature
- it will need to take in user responses and ensure no errors accour
- needs remove the feature it has asked in order not to ask it again
- names to be filttered depending on the response of the user.
- Has a counter to figure out how many questions have been asked.
Have the terminal cleared after each question | low |  | 2021-07-16 | This is a nice to have and is to be completed once all other work has been done
A help file needs to be created for the users | Medium |  | 2021-07-16
-
Bash script | Medium | 2 hours | 2021-07-16 | This is to be done once Python script is complete
-
-
-
-
-
-
-
-
-
-
-
-
-